## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
Team Name | 2211-SWEN-261-04-J error404
Testing Team Name | 2211-swen-261-04-c "Lancer Fanclub"

## Test Plan
User Story | Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Cross Team testing | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button) |  | GDD- 10/2/21- Passed, sign in button is clear on UI |  | GDD- 10/20/21- Passed, sign in button is clear on UI | pass | PF - (11/04/21) YES |  | GDD - 11/9/21, Passed- Clear sign in button when a non-logged in player view the home screen
| Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Sign-in page, with a means to enter a player name. |  | GDD- 10/2/21- Passed, sign in page loads and has clear input area for player name |  | GDD- 10/20/21- Passed, sign in page loads and has clear input area for player name | pass | PF - (11/04/21) YES |  | GDD - 11/9/21, Passed- Sign in button takes players to the sign in screen, where they see a box in which to enter a name
| Given that no one else is using my name when I enter my name containing at least one alphanumeric character and optionally spaces in the sign-in form and click the Sign-in button then I expect the system to reserve my name and navigate back to the Home page. |  | GDD- 10/2/21- Passed, sign in with unreserved name redirects to modified home page. |  | GDD- 10/20/21- Passed, sign in with unreserved and valid name redirects to modified home page. | pass | PF - (11/04/21) YES |  | GDD - 11/9/21, Passed- any name that is at least one character and spaces not already reserved is accepted and takes the user back to the home screen
| Given that I am on the Sign-in page when I enter a name that does not contain at least one alphanumeric character or contains one or more characters that are not alphanumeric or spaces and click the Sign-in button then I expect the system to reject this name and return the Sign-in page. |  | GDD- 10/2/21- Passed, sign in page reloads with new message prompting the user to enter a valid name |  | GDD- 10/20/21- Passed, sign in page reloads with new message prompting the user to enter a valid name | pass | PF - (11/04/21) YES |  | GDD - 11/9/21, Passed- names that are all spaces or contain non-alphanumeric characters are rejected and given a corresponding error message in the sign in screen
| Given that someone else with my name has signed-in when I enter my name in the Sign-in form and click the Sign-in button then I expect the system to reject my sign-in and return the Sign-in page for me to try a different name. |  | GDD- 10/2/21- Passed, sign in page reloads with new message prompting the user to enter a name that is not reserved. |  | GDD- 10/20/21- Passed, sign in page reloads with new message prompting the user to enter a name that is not reserved. | pass | PF - (11/04/21) YES |  | GDD - 11/9/21, Passed- Names that are already reserved are rejected and the user is given a corresponding error message in the sign in screen
| Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.) |  | GDD- 10/2/21- Passed, the names of the players are only visible when signed in |  | GDD- 10/20/21- Passed, the names of the players are only visible when signed in | pass | PF - (11/04/21) YES |  | GDD - 11/9/21, Passed- when signed in, players will see a list of all signed in players other than themselves in scroll list format
| Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons). |  | GDD- 10/2/21- Passed, list of players is shown but prompts the player to sign in to see names, and shows player counts |  | GDD- 10/20/21- Passed, list of players is shown but prompts the player to sign in to see names, and shows player counts | pass | PF - (11/04/21) YES |  | GDD - 11/9/21, Passed- the number of players currently signed in is always shown to users but if a user is not logged in, the scroll list of names instead displays a message prompting the user to log in to see player names
As a Player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page. |  | GDD - 10/4/21- Passed, selection is done by entering the chosen opponents name into the challenge box |  | GDD - 10/20/21- Passed, selection is done by entering the chosen opponents name into the challenge box | Pass | JP; 11-4-2021 - You need to select via a text box? Not a dropdown or link? |  | GDD - 11/9/21, Passed- any valid player can be selected to be challenged by entering their name into the challenge box and clicking the prompted button
| Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player. |  | GDD- 10/4/21- Passed, the starting player is always on the red side and the challenged player on the white |  | GDD- 10/20/21- Passed, the starting player is always on the red side and the challenged player on the white | Pass | JP; 11-4-2021 |  | GDD - 11/9/21, Passed- the player who makes the challenge is set as the red player while the other is set as the white player
| Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message. |  | GDD- 10/4/21- Passed, when a player is in a game, trying to challenge them will return an error informing the user that the player is already in a game |  | GDD- 10/20/21- Passed, when a player is in a game, trying to challenge them will return an error informing the user that the player is already in a game | Pass | JP; 11-4-2021 |  | GDD - 11/9/21, Passed- trying to challenge a logged in player will result in an error message being displayed in the home view informing the user that the player is in a game
| Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View as the White player. NOTE: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game. |  | GDD- 10/4/21- Passed, when a player is challenged, they will automatically be forced into the game upon the first refresh of their home screen. |  | GDD- 10/20/21- Passed, when a player is challenged, they will automatically be forced into the game upon the first refresh of their home screen. | Pass | JP; 11-4-2021 - There's a slight delay in redirection that I observed. |  | GDD - 11/9/21, Passed- upon the first refresh after being challenged, the now white player will be taken into the game. The challengers home view will wait to synchronize with the other players view so both enter the game simulateously.
| Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable. |  | GDD- 10/4/21- Passed, the icon shows that the piece cannot be placed when over a white space |  | GDD- 10/20/21- Passed, the icon shows that the piece cannot be placed when over a white space | Pass | JP; 11-4-2021 |  | GDD - 11/9/21, Passed- when trying to drag a piece to a white space, you are unable to drop a piece
| Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable. |  | GDD- 10/4/21- Passed, the icon shows that the piece cannot be placed when over a space with another piece, friendly or enemy |  | GDD- 10/20/21- Passed, the icon shows that the piece cannot be placed when over a space with another piece, friendly or enemy | Pass | JP; 11-4-2021 |  | GDD - 11/9/21, Passed- when trying to drag a piece to a space occupied by another piece, you are unable to drop a piece
| Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement will be the focus of future stories. |  | GDD- 10/4/21- Passed, the piece is droppable over valid squares, however, upon droping a piece, the player is told that the method is not implemented yet, which is correct. |  | GDD- 10/20/21- Passed, the piece is droppable over valid squares, Upon dropping a piece, the player is asked to submit their move if it is valid or back it up, However, neither of these routes is implemented yet. | Pass | JP; 11-4-2021 |  | GDD - 11/9/21, Passed- upon moving to an open black space, a piece is able to be dropped. In this sprint iteration, the piece can be dropped, but will be reset to its original location if it is not valid
| Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world. |  | GDD- 10/4/21- Passed, both players see the chess board from their own perspective, one on each side. |  | GDD- 10/20/21- Passed, both players see the chess board from their own perspective, one on each side. | Pass | JP; 11-4-2021 |  | GDD - 11/9/21, Passed- both players will see their pieces at the bottom of the screen and the opponents on the other.
As a Player I want an option to resign so that I can end the game at any point | Given that I am in a game when the game has not ended then I should see an option to resign. |  |  |  | GDD- 10/12/21 - Passed, both players see the resign button clearly on the game board screen | Pass | SC - (11/01/21) YES |  | GDD - 11/9/21, Passed- when players are in game, they are able to click the resign button at all points except when they are staging a move to be submitted. Submitting a move or backing up will return the ability to resign
| Given that I see a resign button in a game when I click the resign button then the game should end and the other player should win. |  |  |  | GDD - 10/26/21 - Failed, the game only ends for the player who resigned while the other player never registers that the opponent has resigned. | Pass | SC - (11/01/21) YES |  | GDD - 11/9/21, Passed- when a player resigns on their turn, the opponent is notified upon the first check turn call. If someone resigns not on their turn, they are notified of their victory upon the submission of their move
As a Player I want the game to end either when the opponent cannot move or when all of the opponent's pieces are captured so that I can win the game. | Given that I have captured all of the opponents pieces when I am in a game and make my move then I should win the game and be returned to the home menu with a victory message |  |  |  | GDD - 10/26/21 - Failed, Victory Logic, by means of resignation, lack of moves, or lack of pieces has not yet been implemented in this sprint | Pass | SC - (11/01/21) YES |  | GDD - 11/9/21, Passed- when a move is made that wins a game, the other player will register that they have lost, and on this players next check turn they will be notified of their victory
| Given that the opponent cannot move when I am in a game and make my move then I should win the game and be returned to the home menu with a victory message |  |  |  | GDD - 10/26/21 - Failed, Victory Logic, by means of resignation, lack of moves, or lack of pieces has not yet been implemented in this sprint | Pass | SC - (11/01/21) YES |  | GDD - 11/9/21, Passed- when a move is made that wins a game, the other player will register that they have lost, and on this players next check turn they will be notified of their victory
| Given that my opponent has won when it becomes my turn then I should be returned to the home menu with a defeat message |  |  |  | GDD - 10/26/21 - Failed, Victory Logic, by means of resignation, lack of moves, or lack of pieces has not yet been implemented in this sprint | Pass | SC - (11/01/21) YES |  | GDD - 11/9/21, Passed- if a player is in a losing condition when their turn begins, they are sent to the home view with a message indicating a loss.
| Given that I or my opponent have resigned when we are in a game, then the other player (who did not resign) should win the game. |  |  |  | GDD - 10/26/21 - Failed, Victory Logic, by means of resignation, lack of moves, or lack of pieces has not yet been implemented in this sprint | Pass | SC - (11/01/21) YES |  | GDD - 11/9/21, Passed- the player who resigns first will see a message indicating a loss when returning home, the other player will be returned to the home view with a message indicating a win
| Given that I have won a game, when the game is over, I should see a message that I have won. |  |  |  | GDD - 10/26/21 - Failed, Victory Logic, by means of resignation, lack of moves, or lack of pieces has not yet been implemented in this sprint | Pass | SC - (11/01/21) YES |  | GDD - 11/9/21, Passed- given that a game has ended when a player check for their turn, ended either by the opponents resignation or loss, the player will be returned to the home view with a message indicating victory
As a Player I want the option to either make a move or single/multiple jump wherever legal so that I can choose the best moves to win the game. | Given there is an an empty, adjacent space in front of the piece, when I try to move to that space, it allows me |  |  |  | GDD - 10/20/21 - passed, a single move forward is marked as valid | Pass | MD - (11/01/21) YES |  | GDD - 11/9/21, Passed- a move to an empty black space 1 space away is considered valid
| Given there is an enemy piece, then an empty black space after it, when I try to jump the piece, it vanished from the board and I am available to jump another piece |  |  |  | GDD- 10/26/21- Failed, while the game is able to detect valid jumps and register it as a jump, the piece does not disappear from the current players board. It does however, disappear from the opponents board, so this is likely a minor fix | Pass | MD - (11/01/21) YES Available to jump another piece but jump is automatically completed instead of allowing the player to drag their piece through the two different jumps |  | GDD - 11/9/21, Passed- when there is an enemy piece with an empty black space behind it, you can drag over it and it will be considered a valid move. Submitting the move will remove the piece from both boards. If a double jump is available than attempting to submit partway through will result in an error message being displayed.
| Given that I have made and confirmed my move when I am in a game that is not over then the turn should switch to my opponent, and I should not be able to move my pieces. |  |  |  | GDD - 10/26/21 - Passed, if move is valid than the original and new positions are highlighted, and then when the player presses the submit move button, the active color switches | Pass | MD - (11/01/21) YES |  | GDD - 11/9/21, Passed- upon submitting a move the active player switches and the player who made the move can no longer move pieces.
| Given that me or my opponent have made a move when we are in a game, then the other should see the move that was made. |  |  |  | GDD - 10/26/21 - Passed, if a move is made and submitted then the opponents board updates based on that move with the correct orientation | Pass | MD - (11/01/21) YES |  | GDD - 11/9/21, Passed- upon the first refresh after a move is made, the board is updated to show the moves made by the opponent
| Given there is a piece able to be jumped when I attempt to jump it, it vanishes from the board and my piece moves |  |  |  | GDD - 10/26/21 - Failed, as mentioned for the user availablity acceptance criteria, the Jump implementation has a bug that prevents the users who made the jump from seeing their piece disappear. | Pass | MD - (11/01/21) YES |  | GDD - 11/9/21, Passed- when there is an enemy piece with an empty black space behind it, you can drag over it and it will be considered a valid move. Submitting the move will remove the piece from both boards.
| Given there is ANOTHER piece that is able to be jumped, when I attempt to chain-jump, the other piece vanishes and mine moves |  |  |  | GDD- 10/26/21 - Failed, double jumping functionality was not able to be implemented in this sprint | fail | MD - (11/01/21) NO Only allows for a single jump to submit but completes the double jump automatically. |  | GDD - 11/9/21, Passed- upon completing a chain jump, all jumped pieces disappear from the board as they would for a single jump
| Given that I am in a game with another player when it is either my turn or not then I should not be able to move the other's pieces. |  |  |  | GDD- 10/26/21 - Passed, the game will not allow the player who is not the active color to make any changes to the board, which includes moving pieces | Pass | MD - (11/01/21) YES |  | GDD - 11/9/21, Passed- a player cannot interact with the board while it is not their turn
| Given that I am in a game when I have just made a move then I should have the option to undo the move. |  |  |  | GDD- 10/26/21 - Passed, the game registers that a move is valid and gives the user the option to back up, which undos said move and allows the user to make another | Pass | MD - (11/01/21) YES |  | GDD - 11/9/21, Passed- given that a valid move has been made and staged, the player will be able to submit or backup the move. Backing up the move will return it to its original position and allow another move to be made
As a Player I want to be able to promote my piece to a king once it reaches the other side of the board so that I can move the piece forward or backwards | Given my piece hits the last row WHEN I move it there, then that piece should become a king |  |  |  | GDD - 10/26/21 - Failed, Kinging is not implemented yet, so upon reaching the back row a piece undergoes no change | Pass | MD - (11/01/21) YES |  | GDD - 11/9/21, Passed- a piece that ends its turn on the opponents back row is automatically kinged and gains the ability to jump backwards. The king status is denoted by either stacked pieces or a crown when using a theme pack
| Given I have a king when I go to move it, I should be able to move it 'backward' |  |  |  | GDD- 10/26/21 - Failed, Kinging is not implemented yet, so no movement based on King status can be tested | Pass | MD - (11/01/21) YES |  | GDD - 11/9/21, Passed- a king is able to move and chain jump backwards as well as forwards
As a Player I want to be able to select a theme so that I can change the appearance of my chess board | Given That I am in the theme picker screen when I select a model pack then I expect my current theme to change to that theme. |  |  |  | GDD- 10/20/21 - Passed, after a theme has been selected, going back to the them picker page displays the name of the selected theme | Pass | MD - (11/01/21) YES |  | GDD - 11/9/21, Passed- the stored theme is updated to the chosen theme
| Given That I have selected a theme when I am viewing the game board then I expect to see my current theme. |  |  |  | GDD- 10/20/21 - Passed, after a theme has been selected, opening a game displays a board using each players individual theme | Pass | MD - (11/01/21) YES |  | GDD - 11/9/21, Passed- the chosen theme is applied to the board upon selection and modifies the appearence of the board
As a Player I want to be able to see an image of what each theme will look like so that I can choose my favorite theme from the options given | Given That I am in the web application when I am viewing the theme picker screen then I expect to see my current theme. |  |  |  | GDD- 10/20/21 - Passed, when viewing the theme selections screen, the name of the current theme is displayed | Pass | MD - (11/01/21) YES |  | GDD - 11/9/21, Passed- the text at the top of the theme selector screen shows the name of the current theme
| Given That I am in the web application when I am viewing the theme picker screen then I expect to see each possible theme and their name |  |  |  | GDD- 10/20/21 - Passed, when view the theme selection screen, each possible theme is labeled with a clear and distinctive name | Pass | MD - (11/01/21) YES |  | GDD - 11/9/21, Passed- each theme is shown along with an image of what the board looks like with it applied
| Given That I am in the web application when I am viewing the theme picker screen then I expect to see a small image displaying a preview of what the each theme will look like. |  |  |  | GDD-10/20/21 - Passed, when in the theme picker screen, there are images of the board as it would look in play from the red perspective next to each theme | Pass | MD - (11/01/21) YES |  | GDD - 11/9/21, Passed- each theme is shown along with an image of what the board looks like with it applied
As a Player I want to be able to see a clear button for the theme screen so that I can click it and go to the theme selection screen. | Given That I am in the game or home screen when I click the theme button then I expect to be taken to the theme picker screen. |  |  |  | GDD- 10/20/21 - Passed, when in the home or game screen there is a clear button to take you to the home screen | Pass | MD - (11/01/21) YES |  | GDD - 11/9/21, Passed- in both the game and home view a button to choose the theme is clearly displayed to the user and takes them to the selection screen upon being clicked
As a Player I want to be able to open a help menu over the board when I select the help button so that I can review the rules. | Given that I am in the Game View when it is my turn then I expect to see a button for the help menu |  |  |  |  | Pass | MD - (11/01/21) YES Help menu could also be titled help |  | GDD - 11/9/21, Passed- a clearly indicated button for player help is shown in the nav bar
| Given that I have clicked the help menu button when it is my turn then I expect to be taken to the player help menu |  |  |  |  | Pass | MD - (11/01/21) YES |  | GDD - 11/9/21, Passed- upon selecting the player help option from the nav bar, the player is taken to the help screen
As a Player I want to see explanations of legal movement, single/multiple jumps, and kinging so that I understand how to play and win checkers. | Given that I have opened the player help menu when I am in a game then I expect to see a list of rules and strategies to teach me how to play checkers. |  |  |  |  | Pass | MD - (11/01/21) YES |  | GDD - 11/9/21, Passed- the player help menu explains the basic rules of checkers along with moves and win conditions. Pictures are added to enhance the information given to the user
| Given that I have opened the player help menu when I click the return to game button then I expect to be taken back to the board as it was when I entered the help menu |  |  |  |  | Pass | MD - (11/01/21) YES |  | GDD - 11/9/21, Passed- upon exiting the help menu, the player is return to the screen they started on, whether that be the home screen or game board
As a Player I want to have some indicator displayed to my opponent when I am in the help menu so that my opponent knows that I am getting help rather than having left. | Given that my opponent is in the player help menu when I am in the game view and it is not my turn then I expect to see a message informing me that the opponent is in the player help menu |  |  |  |  | Not tested for cross team | N/A |  | GDD - 11/9/21, Passed- when the opponent is taking their turn and is spending time in the help menu or theme menu, the board will refresh to notify the user that they opponent is in a menu. The notification disappears upon the first refresh where the opponent is not in menu.
NOTES: MD - Internal 500 error when a player tries to use the sign out button during the game
PF - Crashed when one player was making a move and another was choosing a theme